## Sprint_1
📋 Sprint 1 — QA Workshop Release Planning
👤 Omar Kandeel
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1 | 5 | 5 | 0 | ✅ Done
Day 2 | 0 | 0 | 0 | ✅ Done
Day 3 | 0 | 0 | 0 | ✅ Done
Day 4 | 5 | 3 | 2 | ✅ Done
Day 5 | 2 | 0 | 2 | ✅ Done
Day 6 | 2 | 5 | -3 | ✅ Done
Day 7 | 0 | 4 | -4 | ✅ Done
📊 TOTAL | 14 | 17 | -3
👤 Abdelrahman Yasser
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1 | 5 | 5 | 0 | ✅ Done
Day 2 | 0 | 0 | 0 | ✅ Done
Day 3 | 0 | 0 | 0 | ✅ Done
Day 4 | 0 | 0 | 0 | ✅ Done
Day 5 | 3 | 0 | 3 | ⏳ Not Started
Day 6 | 3 | 0 | 3 | ⏳ Not Started
Day 7 | 1 | 0 | 1 | ⏳ Not Started
📊 TOTAL | 12 | 5 | 7
👤 Amr
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1 | 5 | 5 | 0 | ✅ Done
Day 2 | 0 | 0 | 0 | ✅ Done
Day 3 | 0 | 0 | 0 | ✅ Done
Day 4 | 3 | 3.5 | -0.5 | 🔄 In Progress
Day 5 | 2 | 1 | 1 | ⏳ Not Started
Day 6 | 3 | 4 | -1 | ⏳ Not Started
Day 7 | 3 | 5 | -2 | ⏳ Not Started
📊 TOTAL | 16 | 18.5 | -2.5
👤 Amira
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1 | 6 | 6 | 0 | ✅ Done
Day 2 | 0 | 0 | 0 | ✅ Done
Day 3 | 2 | 0.5 | 1.5 | ✅ Done
Day 4 | 2 | 2 | 0 | ✅ Done
Day 5 | 0 | 0 | 0 | ✅ Done
Day 6 | 3 | 4 | -1 | ✅ Done
Day 7 | 1 | 2.5 | -1.5 | ✅ Done
📊 TOTAL | 14 | 15 | -1
👤 Aya
Day | Planned Hours |  | Remaining Hours | Status | Task / Notes
Day 1 | 6 | 6 | 0 | ✅ Done
Day 2 | 0 | 0 | 0 | ✅ Done
Day 3 | 0 | 0 | 0 | ✅ Done
Day 4 | 2 | 1 | 1 | ✅ Done
Day 5 | 3 | 3 | 0 | ✅ Done
Day 6 | 3 | 4.5 | -1.5 | ✅ Done
Day 7 | 2 | 2 | 0 | ✅ Done
📊 TOTAL | 16 | 16.5 | -0.5
📈 Sprint 1 — Team Hours Overview
Team Member | Planned Hours | Actual Hours
Omar Kandeel | 14 | 17
Abdelrahman Yasser | 12 | 5
Amr | 16 | 18.5
Amira | 14 | 15
Aya | 16 | 16.5

## 📊 Dashboard
📊 QA Workshop — Release Planning Dashboard
Team Hours Summary Across All Sprints
| Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | 📊 Totals
Team Member | Planned | Actual | Planned | Actual | Planned | Actual | Total Planned | Total Actual | Variance
👤 Omar Kandeel | 14 | 17 | 0 | 0 | 0 | 0 | 14 | 17 | -3
👤 Abdelrahman Yasser | 12 | 5 | 0 | 0 | 0 | 0 | 12 | 5 | 7
👤 Amr | 16 | 18.5 | 0 | 0 | 0 | 0 | 16 | 18.5 | -2.5
👤 Amira | 14 | 15 | 0 | 0 | 0 | 0 | 14 | 15 | -1
👤 Aya | 16 | 16.5 | 0 | 0 | 0 | 0 | 16 | 16.5 | -0.5
📊 GRAND TOTAL | 72 | 72 | 0 | 0 | 0 | 0 | 72 | 72 | 0

## Sprint_2
📋 Sprint 2 — QA Workshop Release Planning
👤 Omar Kandeel
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
👤 Abdelrahman Yasser
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
👤 Amr
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
👤 Amira
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
👤 Aya
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
📈 Sprint 2 — Team Hours Overview
Team Member | Planned Hours | Actual Hours
Omar Kandeel | 0 | 0
Abdelrahman Yasser | 0 | 0
Amr | 0 | 0
Amira | 0 | 0
Aya | 0 | 0

## Sprint_3
📋 Sprint 3 — QA Workshop Release Planning
👤 Omar Kandeel
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
👤 Abdelrahman Yasser
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
👤 Amr
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
👤 Amira
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
👤 Aya
Day | Planned Hours | Actual Hours | Remaining Hours | Status | Task / Notes
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
📊 TOTAL | 0 | 0 | 0
📈 Sprint 3 — Team Hours Overview
Team Member | Planned Hours | Actual Hours
Omar Kandeel | 0 | 0
Abdelrahman Yasser | 0 | 0
Amr | 0 | 0
Amira | 0 | 0
Aya | 0 | 0