## Release#2
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments
1 | 27 | 27 | 78 |  |  |  | E2E workflow draft | 100%
2 | 27 | 27 |  |  |  |  | SRS update | 100%
3 | 29 | 27.5 |  |  |  |  | CRS update | 100%
4 | 41 | 39 |  |  |  |  | RTM | 100%
5 | 51 | 48 |  |  |  |  | TC draft | 100%
6 | 64 | 62
7 | 78 | 78
Risks
ID | Topic | Probability | Impact | Description | Handling | Actions
Risk_1 | Tech | 2 | 5 | NO Time Tolerance | Accept
5
ID | Initiator | Probability | Impact | Description | Handling | Actions
1 |  |  |  | One time member was sick | Accept | reassign tasks
s

## Release#1
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments
1 | 18 | 15 | 48 |  |  |  | CRS | 100%
2 | 20 | 17 |  |  |  |  | SIQ | 100%
3 | 23 | 23.5 |  |  |  |  | CMP | 100%
4 | 23 | 25 |  |  |  |  | PMP | 100%
5 | 27 | [5 empty] | SRS | 100%
6 | 37 | [5 empty] | Risk sheet | 100%
7 | [6 empty] | Jira | 100%
Risks
ID | Topic | Probability | Impact | Description | Handling | Actions
Risk_1 | Tech | 5 | 3 | Lack of experience | Mitigate | Provided learning crash course
5
ID | Initiator | Probability | Impact | Description | Handling | Actions
Avoid